Launching Countdown Checklist

You’ve set up your launch step-by-step, now let’s make sure you have all your “I’s” dotted and “t’s” crossed and test all your technology.

For the purpose of an example, we’re setting dates as if you offered your challenge or webinar starting on a Monday, the week of August 24th.

REGISTER PARTICIPANTS FOR YOUR CHALLENGE OR WEBINAR

- Finalize your challenge or webinar including:

  - Challenge or Webinar Name

  - Challenge or Webinar Promise

  - Challenge or Webinar 5 Advertising Bullet points.

  - For each day of a challenge, you’ll need:

    - Name for the day

    - Short description & mini-promise

    - Challenge question

- Set up an autoresponder account if you do not have one

- Create your landing page & thank you page – you can do this in your autoresponder, on your website or in LeadPages

- Write your Welcome Email & upload it to your autoresponder. Make sure it is connected to your landing/thank you page.

- Ask a friend to register using your landing page url so you can test this. Make sure they receive your welcome email.

- As soon as you have these first steps done, you can start sharing your landing page link in social media posts and in your emails! Start getting folks registered ASAP!

- Create a Warm-Up Email Funnel in your autoresponder (start emailing 11 days prior - by August 13th)

- Send an Re-Engagement Email if you have changed niches or cobbled together an email list (ASAP)

- Write your Invite Email Funnel if you have an email list (start emailing your list 6 days prior - by August 18th)

- Double-check that your Email Funnels are published in your autoresponder.

- Add Facebook Headers that have info on your challenge or webinar on your personal page and in your Facebook Group that say “click here for more info” then add a description with your landing page link.

DELIVERING YOUR CHALLENGE OR WEBINAR

- Make sure you have a Facebook Community Group set up

- Create your Challenge or Webinar Workbook/Guide (at least 1 day prior - by August 23rd)

  - Double-check that you added the link to it in your warm-up emails. You can add it to your media library on your website (simple but bogs down your website) or to a cloud storage platform like Amazon S3 (recommended).

- Bullet point out your Challenge Script or Webinar Template (at least 1 day prior - by August 23rd)

  - If you are doing a webinar, you’ll also want to have a power point presentation done.

- Write out your pitch for Challenge Day 4 and re-pitch for Day 5 (by day 3 of your challenge - by August 27th)

- Practice a Facebook Livestream in your Facebook Group to make sure your technology is working

  - If you are having 2 presenters, you are going to need to use Zoom and broadcast to Facebook or an app like belive.tv. Make sure you have these apps integrated within your Facebook Group and have a backup plan in case something goes wrong.

- Consider having a friend or assistant help you answer questions in the chatbox during your Facebook Livestreams for your challenge or on your webinar.

  - Train your assistant! Assume they know nothing. For our team, we prepare a document with all the possible questions (and our answers) that we anticipate they’ll see in the chatbox so they know exactly how to answer.

- Make sure you add your replay links to your emails each day or upload them to a replay page so all are in one place.

SELL YOUR ONLINE PROGRAM

- Finalize your online program including:

  - Online Program Name

  - Promise

  - 5-8 Steps

  - Pain points

  - Benefits

  - Program Advertising Bullet Points

  - Price

  - Structure/What’s Included

  - Bonuses

  - Cancellation Policy

By the time you do your pitch, you’ll want to have:

- Create your online program sales page using our Online Program Sales Page Template by your pitch date (most of challenges pitch on Day 4 - on August 27th)

  - Insert and test your registration/buy button using Paypal or payment processor

  - If you are offering a payment plan or fast-action discount, you’ll need to have this set up as well.

- Set up a Calendar Link for Clarity/Sales Calls so folks can talk to you about joining your online program and make sure you have dates available (by Day 4 - by August 27th)

- Write your Post-Pitch Sales Email Funnel & add it to your autoresponder (which starts 7 days after - on August 30th)

- Double check you re-published your Email Funnels

DELIVERING YOUR ONLINE PROGRAM

- If you are having group calls, set up your Zoom or webinar link.

- Create a Facebook Buyer’s Group if you are using one.

- Write your Buyers’ Delivery Funnel & upload to your autoresponder (by Day 4 - have at least the first email this by August 27th when people can start buying your program)

- Create your Program Delivery Page where you will upload replays and share any documents for your program. You can do this in a membership program app, as a password protected page on your website or even in “Units” in your Facebook Buyers’ Group.

  - It’s nice to have a Welcome Page that explains the next steps in your program (ideally this happens by Day 4 -  by August 27th but you can have it up by cart close)

- Create a Vimeo (or YouTube) account so you can upload your replays – make sure they are not visible to the public. You’ll then add your replay links onto your Program Delivery Page as you deliver your course.

BUILD YOUR LIST - ongoing

- Research & join Facebook Groups for your niche/avatar

- Start friending people on social media using our PM scripts

- Start priming your tribe for your launch with fun posts & FB/IG Lives based on your 5-8 steps/10 complaints/10 changes

Once you’ve done a launch a few times, it gets much easier.  And after your launch is all done it’s time for the best part – working with your clients!